## Risk Register
id | risk_name | category | description | department | probability | impact | date_identified | status | owner
R001 | Unauthorized access to client database | Cybersecurity | Legacy access permissions not revoked after employee offboarding | IT Security | 3 | 5 | 2026-01-12 | Open | J. Silva
R002 | Late regulatory reporting to Bank of Portugal | Compliance | Manual data collection process causes delays in monthly submissions | Compliance | 4 | 4 | 2026-01-15 | Open | M. Costa
R003 | Vendor data breach exposure | Third-Party | Third-party payment processor lacks SOC2 certification | Procurement | 2 | 5 | 2026-01-18 | Open | A. Ferreira
R004 | Segregation of duties violation | Internal Controls | Same employee can both approve and execute wire transfers | Operations | 3 | 4 | 2026-01-20 | Mitigated | J. Silva
R005 | Outdated business continuity plan | Operational Resilience | BCP not tested or updated in over 18 months | Risk Management | 3 | 3 | 2026-01-22 | Open | M. Costa
R006 | Phishing susceptibility | Cybersecurity | Simulated phishing campaign showed 22% click-through rate | IT Security | 4 | 3 | 2026-01-25 | Open | A. Ferreira
R007 | KYC documentation gaps | Compliance | Sample audit found 8% of client files missing updated ID documents | Compliance | 3 | 4 | 2026-01-28 | Open | M. Costa
R008 | Unencrypted data in transit | Cybersecurity | Legacy internal reporting tool transmits data without TLS | IT Security | 2 | 5 | 2026-02-01 | Open | J. Silva
R009 | Single point of failure in payment system | Operational Resilience | No failover server configured for core payment processing | Operations | 2 | 5 | 2026-02-03 | Open | A. Ferreira
R010 | Sanctions screening list outdated | Compliance | Screening database not synced with latest OFAC update for 3 weeks | Compliance | 3 | 5 | 2026-02-05 | Mitigated | M. Costa
R011 | Excessive privileged access accounts | Cybersecurity | 47 accounts hold admin rights, exceeding least-privilege policy | IT Security | 4 | 4 | 2026-02-08 | Open | J. Silva
R012 | Fraudulent account takeover pattern | Fraud | Spike in ATO attempts linked to credential stuffing | Fraud Prevention | 4 | 4 | 2026-02-10 | Open | A. Ferreira
R013 | Missing DPO sign-off on new vendor | Data Privacy | New marketing vendor onboarded without GDPR data processing agreement | Legal | 2 | 4 | 2026-02-12 | Open | M. Costa
R014 | Inadequate incident response testing | Cybersecurity | Tabletop exercise not conducted in current fiscal year | IT Security | 3 | 4 | 2026-02-14 | Open | J. Silva
R015 | Manual reconciliation errors | Operational | Spreadsheet-based reconciliation caused 3 material discrepancies | Operations | 4 | 3 | 2026-02-16 | Mitigated | A. Ferreira
R016 | Critical vendor concentration risk | Third-Party | 80% of cloud infrastructure hosted with single provider | Procurement | 2 | 5 | 2026-02-18 | Open | M. Costa
R017 | Weak password policy enforcement | Cybersecurity | 12% of accounts non-compliant with complexity requirements | IT Security | 3 | 3 | 2026-02-20 | Open | J. Silva
R018 | Delayed patch management | Cybersecurity | Critical CVE unpatched on 6 production servers for 30+ days | IT Security | 3 | 5 | 2026-02-22 | Open | A. Ferreira
R019 | Insufficient staff training on AML red flags | Compliance | Only 60% of frontline staff completed annual AML training | Compliance | 3 | 3 | 2026-02-24 | Open | M. Costa
R020 | Shadow IT usage | Cybersecurity | Unapproved SaaS tool used by marketing team to store client data | IT Security | 3 | 4 | 2026-02-26 | Open | J. Silva
R021 | Inaccurate risk appetite reporting | Governance | KRI dashboard uses outdated formula for one metric | Risk Management | 2 | 3 | 2026-02-28 | Closed | M. Costa
R022 | Third-party access not time-limited | Third-Party | Contractor retains system access 60 days post-contract end | Procurement | 3 | 4 | 2026-03-02 | Open | A. Ferreira
R023 | Data retention policy non-compliance | Data Privacy | Customer records retained beyond regulatory limit in archive system | Legal | 2 | 4 | 2026-03-04 | Open | M. Costa
R024 | Weak MFA coverage | Cybersecurity | MFA not enforced for 15% of remote access accounts | IT Security | 3 | 5 | 2026-03-06 | Open | J. Silva
R025 | Undetected duplicate payments | Operational | Control gap allows duplicate invoice payments under threshold | Operations | 2 | 3 | 2026-03-08 | Mitigated | A. Ferreira
R026 | Insider trading monitoring gap | Compliance | Trade surveillance system has 4-hour reporting lag | Compliance | 2 | 5 | 2026-03-10 | Open | M. Costa
R027 | Cloud storage misconfiguration | Cybersecurity | One S3-equivalent bucket found with public read access | IT Security | 2 | 5 | 2026-03-12 | Mitigated | J. Silva
R028 | Outdated vendor risk assessments | Third-Party | 35% of critical vendors have assessments older than 12 months | Procurement | 4 | 3 | 2026-03-14 | Open | A. Ferreira
R029 | Business email compromise attempt | Fraud | CFO impersonation email requesting urgent wire transfer | Fraud Prevention | 3 | 5 | 2026-03-16 | Mitigated | J. Silva
R030 | Inconsistent access recertification | Internal Controls | Quarterly recertification skipped for one department | Operations | 3 | 3 | 2026-03-18 | Open | M. Costa
R031 | Unmonitored API endpoints | Cybersecurity | Two internal APIs found without rate limiting or logging | IT Security | 3 | 4 | 2026-03-20 | Open | J. Silva
R032 | Regulatory change not yet implemented | Compliance | New DORA incident reporting requirement not yet operationalized | Compliance | 4 | 4 | 2026-03-22 | Open | M. Costa
R033 | Weak vendor exit strategy | Third-Party | No documented data return/deletion process for terminated vendors | Procurement | 2 | 4 | 2026-03-24 | Open | A. Ferreira
R034 | Excessive dormant accounts | Cybersecurity | 230 user accounts inactive for 90+ days remain enabled | IT Security | 3 | 3 | 2026-03-26 | Open | J. Silva
R035 | Inadequate logging retention | Cybersecurity | Security logs purged after 30 days, below 1-year policy requirement | IT Security | 3 | 4 | 2026-03-28 | Open | A. Ferreira
R036 | Unclear escalation ownership | Governance | Incident escalation matrix has no named owner for Tier 2 alerts | Risk Management | 2 | 3 | 2026-03-30 | Closed | M. Costa
R037 | Suspicious transaction pattern | Fraud | Structuring pattern detected across linked accounts | Fraud Prevention | 4 | 4 | 2026-04-01 | Open | J. Silva
R038 | Non-compliant data transfer to third country | Data Privacy | Client data transferred to processor outside adequacy framework | Legal | 2 | 5 | 2026-04-03 | Open | M. Costa
R039 | Unpatched end-of-life software | Cybersecurity | Legacy reporting server running unsupported OS version | IT Security | 4 | 5 | 2026-04-05 | Open | A. Ferreira
R040 | Inadequate change management approval | Internal Controls | Production code deployed without required second approver | Operations | 3 | 4 | 2026-04-07 | Mitigated | J. Silva